## Sheet1
Project Status Check Report Group - 1
Sl no. | Employee ID | Name | Domain | Module | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-06 | 2022-03-07 | 2022-03-08
1 | 2489588 | Alaparthi Sai Madhavi | E-Medicare | Contact,Payment,Manage Products | ER Diagram ,Database, Division of domain | Front end-Contact-Completed | Frontend-View Products-Completed,Payment-Working | Payment-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
2 | 2489569 | Abhijit Jawale | E-Medicare | Home,Categories | ER Diagram ,Database, Division of domain | Front end-Home-started | Front-Cate-Antipyretics-Completed,Admin-login-Working | Admin-login-Working | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Documentation | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
3 | 2487449 | Nilesh Tale | E-Medicare | Allproducts,Logout | ER Diagram ,Database, Division of domain | Front end-Login-Completed | Frontend-All products-Completed,Cart-Working | Cart-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
4 | 2489600 | Khdija Khan | E-Medicare | Home,Signup,checktq | ER Diagram ,Database, Division of domain | Front end-Home,Signup-started | Front-Cate-Antiboitics-Completed,Signup-Validation-Working | Signup-Validation-Working | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | PPT | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
5 | 2484251 | Sahil Khan | E-Medicare | Home,Categories,About ,Contact | ER Diagram ,Database, Division of domain | Front end-Home-started | Front-Cate-Analgesics-Completed,Admin-login-Working | Admin-login-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Documentation | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
6 | 2491107 | Byrraju Raju | E-Medicare | Contact,Payment,Manage Products | ER Diagram ,Database, Division of domain | Front end-About-Completed | Frontend-View Products-Completed,Payment-Working | Payment-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
7 | 2487232 | Abhishek.GR | E-Medicare | UserLogin,AdminLogin,Signup | ER Diagram ,Database, Division of domain | Front end-Login-Completed | Frontend-User-login-Completed,Signup-Validation-Working | Signup-Validation-Working | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
8 | 2488299 | Kajal Gaikwad | E-Medicare | Allproducts,Cart,Logout | ER Diagram ,Database, Division of domain | Front end-Contact-Completed | Frontend-All products-Completed,Cart-Working | Cart-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
9 | 2490447 | Tupili Sai | E-Medicare | About | ER Diagram ,Database, Division of domain | Front end-About-Completed | Frontend-View Products-Completed,Payment-Working | Payment-Completed | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation
10 | 2488331 | Deepika Sivaraj | E-Medicare | Signup | ER Diagram ,Database, Division of domain | Front end-Signup-Completed | Frontend-View Signup-Validation-Working | Signup-Validation-Working | Backend-Json server | Backend-Json server | Error Solving,Routing | Modifications in frontend | Postman-testing | Modifications and Jasmine testing | Jasmine testing,Presentation Preparation

## Sheet2
Project Name : E-Medicare
Group Number - 1
Team Lead & Frontend Lead- Alaparthi Sai Madhavi
Backend Lead - Abhishek.GR

## Sheet3
Status Meeting Group - 1
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-03-10 | 12:30 | a | 3:30 | a | 6:00 | a
2022-03-11 | 9:30 | a | 1:00 | a | 6:20 | a
2022-03-12 | 9:30 | a | 2:00 | a | 6:10 | a
2022-03-13 | 10:30 | a | 2:30 | a | 6:00 | a
2022-03-14 | 9:30 | a | 2:30 | a | 5:30 | a
2022-03-15 | 9:30 | a | 3:00 | a | 6:00 | a
2022-03-16 | 9:30 | a | 2:30 | a | 6:00 | a
2022-03-17 | 10:50 | a | 3:00 | a | 6:00 | a
2022-03-18 | 11:00 | a | 3:30 | a | 6:00 | a
2022-03-19 | 9:30 | a | 1:30 | a | 6:30 | a